PROJECT OVERVIEW: NATIONAL VISIBILITY STRATEGY DEVELOPMENT

Purpose:
To develop a comprehensive, strategic plan over the next eight months that will position ittle Pink as a nationally recognized organization, expanding awareness of our mission and impact. This initiative will engage a committee of marketing, branding, and PR executives to research, analyze, and create a roadmap for achieving national visibility.

Objectives:

- Define what national visibility means for our organization and set measurable success metrics.

- Analyze current brand perception and competitive landscape to identify positioning opportunities.

- Develop a compelling brand narrative and messaging framework for national audiences.

- Establish a media and PR outreach strategy, including a targeted press kit and key story angles.

- Identify and outline strategic corporate, media, and influencer partnerships.

- Finalize a 12-month execution plan for implementation post-project completion.

Project Timeline & Key Milestones:

- Month 1: Define vision, goals, and baseline research on current visibility.

- Month 2: Competitive benchmarking and audience analysis.

- Month 3: Develop brand messaging and storytelling strategy.

- Month 4: Build national PR and media outreach framework. Plan for capacity building.

- Month 5: Identify strategic partnerships and sponsorship opportunities.

- Month 6: Develop influencer and ambassador engagement strategy.

- Month 7: Finalize all components and refine the national visibility plan.

- Month 8: Present the finalized plan to leadership for review and approval.

Expected Outcomes:
By the end of eight months, we will have a fully developed strategy that includes:

- A structured national brand messaging guide.

- A clear media engagement and PR strategy.

- A corporate sponsorship and influencer outreach plan.

- A detailed 12-month roadmap for execution.

### Month 1: Establishing Vision, Goals & Success Metrics

Key Focus: Define national visibility, set objectives, and assess the current state.

- Kickoff meeting with committee members (roles, expectations, goals).

- Define what "national visibility" means for the organization.

- Set measurable success metrics (e.g., media reach, audience growth, partnerships).

- Conduct an internal brand and communication audit.

- Assign committee members research tasks on current brand perception.

Deliverable: Clear visibility goals, success metrics, and an internal brand audit report.

### Month 2: Competitive Benchmarking & Audience Research

Key Focus: Analyze competitors and define target audiences.

- Identify 3-5 successful national non-profits for comparison.

- Research their media presence, partnerships, and visibility strategies.

- Define key target audiences (media, donors, corporate partners, families).

- Conduct surveys or focus groups (if possible) for audience insights.

- Assess social media and digital engagement trends.

Deliverable: Competitive analysis report and target audience profiles.

### Month 3: Brand Messaging & Storytelling Framework

Key Focus: Develop the national brand narrative and messaging strategy.

- Define the core brand story and positioning for national reach.

- Develop key messaging for different stakeholders (media, donors, public).

- Create a storytelling framework focused on impact, testimonials, and mission.

- Begin drafting foundational content for press materials.

Deliverable: Core messaging framework and storytelling guide.

### Month 4: PR & Media Strategy Development

Key Focus: Build a media engagement strategy.

- Identify top-tier media outlets and journalists aligned with the mission.

- Develop a PR outreach strategy (earned media, op-eds, TV/radio opportunities).

- Create a draft press kit, including fact sheets, impact stories, and leadership bios.

- Outline a thought leadership strategy (panel appearances, articles, interviews).

Deliverable: Media target list, press kit draft, and PR strategy outline.

### Month 5: Corporate & Strategic Partnerships Plan

Key Focus: Identify national sponsors, donors, and brand collaborations.

- Define ideal corporate partners and their alignment with the mission.

- Develop a sponsorship framework (tiered sponsorships, benefits, expectations).

- Identify potential non-profit collaboration partners for increased reach.

- Draft corporate sponsorship outreach materials.

Deliverable: Corporate partnership framework and outreach materials.

### Month 6: Influencer & Ambassador Strategy

Key Focus: Engage public figures, influencers, and brand advocates.

- Identify potential celebrity ambassadors, influencers, and key advocates.

- Define an engagement strategy (social media collaborations, endorsements).

- Develop outreach messaging and relationship-building approach.

- Plan a potential ambassador campaign launch timeline.

Deliverable: Influencer and ambassador engagement plan.

### Month 7: Finalizing the National Visibility Plan

Key Focus: Refine and integrate all components into a cohesive strategy.

- Review and finalize brand messaging and PR strategy.

- Finalize corporate and influencer engagement plans.

- Develop an integrated 12-month execution timeline for implementation.

- Create a strategy presentation for board approval.

Deliverable: Completed National Visibility Plan ready for board review.

### Month 8: Presentation & Pre-Implementation Planning

Key Focus: Secure board approval and transition to execution phase.

- Present the finalized strategy to the board for feedback and approval.

- Outline resource needs, budget considerations, and timeline adjustments.

- Establish accountability and leadership for implementation.

- Assign early action items for implementation kickoff.

Deliverable: Board-approved strategy and roadmap for execution.

### Final Deliverables at the End of 8 Months:

✔ National Visibility Strategy Document
✔ Brand Messaging & Storytelling Guide
✔ Media & PR Outreach Plan
✔ Corporate Sponsorship & Partnership Framework
✔ Influencer & Ambassador Engagement Plan
✔ 12-Month Execution Roadmap

This extended timeline allows for thorough research, strategy refinement, and strong stakeholder buy-in, ensuring the non-profit is fully prepared for a high-impact national visibility push.